## Sheet1
Comments Description | Classification | ETA (Hours) | Status | Note
General bug in all pages: White section appears in the bottom of the app while trying to scroll on IOS phones. | Bug | 4
Checkout Page: Soemtimes this page keeps loading for long time and the user is not able to do something. To be checked and tested on ios and android. | Bug | 4
Product Details Page, Brochure: The user is not able to download the pdf on IOS phones. On Android generates Error. | Bug | 4
Product List Page: all the products cards should have the same height even if the product has discount or not | Bug | 4
Contact Us Page: Fix the telephone number alignment in arabic | Bug | 0.5
Footer: Add letter "s" to work "Control" to be "Controls" and in Arabic كونترولز | Bug | 0.25
Categories Page: Change the way of showing categories if the categories number is more than 3 ( Less than 3 every row has one category but if the categories number is more than 3 so every row has more than category | New Request | 4
Product Details Page, Product Images Section: Once the user clicks to maximize the view of specific image, the user should able to zoom the image in and out | New Request | 4
Header: Add button menu to be shown in all pages except the home page | New Request | 2
Service Request Page: Ac Issues drop down should has one more option which is "Others". Once the user select this option the app should show a new text field that lets the user to enter his/her issues. | New Request | 2
Home Page: Remove all empty or white sections and let the main 2 images (online store & Our Services) fill in the whole screen | New Request | 1
Custom Register Page: Add "City" text field and to be mandatory as well. | New Request | 1
Home Page: Change Online Store Section Background Image | New Request | 0.5
Categories Page: Specific Icon should appear for each category | New Request | 0.5
Product List Page, Product Card: remove the description from card and just keep the name of the product | New Request | 0.5
Product List Page, Product Card: Change the color of the add to whishlist button to be red and the border to be more thiner. | New Request | 0.5
Product Details Page, Description Section: Replace the content of the description section by the one that appears in the description tab at the same page. | New Request | 0.5
Product Details Page, Additional Information Tab: In this tab should appear only the height and the dimension of the product. | New Request | 0.5
Splash Screen: Add this sentence to the logo"أقوى تكييف في المملكة" | New Request | 0.5
Home Page: Remove Banner | New Request | 0.5
Product List Page, Product Card: Change the color of the new price to be red if the product has discount. | New Request | 0.5
Product Details Page, Product Images Section: Let the whole image in this section to be clickable, once the user clicks on any position on this image a new window opens to show the image in larger size. | New Request | 0.5
Product Details Page, Description Section: Change the place of the label "Availability" and put it under the quantity label + adjusting its font size | New Request | 0.5
Product Details Page, Prices: Change the color of the new price to be red if the product has discount. | New Request | 0.5
Checkout Page, Coupon: Replace the word "Coupon" to be "Promo" in the text field and the button as well. "Apply Coupon" to "Apply" | New Request | 0.5
Product Details Page, Prices: Change the Label "Price" to new "New Price" if the product has new price. | New Request | 0.25
Product Details Page, Product Images Section: Remove the magnifier icon from the top left ( en) and top right ( ar) . | New Request | 0.25
Checkout Page: Switch places of the "Checkout" Button and "Continue Shopping" Button. | New Request | 0.25
Checkout Page: Change color of the checkout button to be blue as continue shopping's button | New Request | 0.25
Compare Feature: To be checked if it is applicable on mobile version | New Request | 1